## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
Secure Communication Project
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Caleb Knapp
Project Start Date: | 2022-01-25 |  |  |  |  | January | [6 empty] | February | [27 empty] | March
Scrolling Increment: | 0 | time axis 2022-01-25 to 2022-03-21
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-01-25 to 2022-03-21
Sprint 1
Create Initial Requirements Document | On Track | All | 100% | 2022-01-25 | 8
Sprint 2
Come up with name | Low Risk | All |  | 2022-02-02 | 3
Create master page | Low Risk | Himprawa Khattri | 0% | 2022-02-05 | 1
Create landing page | Low Risk | Himprawa Khattri | 0% | 2022-02-06 | 3
Create user information tables | Low Risk | Mason Phillips, Timothy de Jesus | 0% | 2022-02-09 | 3
Create user registration page | Low Risk | Himprawa Khattri | 0% | 2022-02-12 | 4
Sprint 3
User search feature |  | Timothy de Jesus, Himprawa Khattri | 0% | 2022-02-16 | 5
Friends list feature |  | Himprawa Khattri | 0% | 2022-02-21 | 3
Make channel framework |  | Mason Phillips, Timothy de Jesus | 0% | 2022-02-16 | 7
Create message dashboard |  | Himprawa Khattri | 0% | 2022-02-24 | 6
Sprint 4
One-on-one communication |  | Mason Phillips, Timothy de Jesus | 0% | 2022-03-02 | 7
Notification of new messages |  | Timothy de Jesus, Himprawa Khattri | 0% | 2022-03-09 | 3
Make admin dashboard |  | Mason Phillips, Himprawa Khattri | 0% | 2022-03-09 | 5
Make first presentation material |  | All |  | 2022-03-02 | 13
Sprint 5
Group communication |  | Mason Phillips, Timothy de Jesus | 0% | 2022-03-16 | 7
Ability to join multiple channels |  | All | 0% | 2022-03-23 | 4
Ability to break out from groups |  | Timothy de Jesus, Himprawa Khattri | 0% | 2022-03-27 | 3
Sprint 6
Shoulder surfing protection |  | Mason Phillips, Himprawa Khattri | 0% | 2022-03-30 | 14
User icons |  | Himprawa Khattri | 0% | 2022-03-30 | 14
Sprint 7
Optimize for mobile devices |  | All | 0% | 2022-04-13 | 14
Sprint 8
Make final presentation material |  | All | 0% | 2022-04-27 | 7
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-04-13 |  |  |  |  | April | [20 empty] | May | [27 empty] | June
Scrolling Increment: | 1 | time axis 2022-04-14 to 2022-06-08
Milestone description | Category | Assigned to | Progress | Start | Days | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
TITLE 1
Task 1 | Goal | Name | 25% | 2022-04-13 | 3 | T: 2; F: 2
Task 2 | Milestone |  |  | 2022-04-18 | 1 | bar: M
Task 3 | Low Risk |  | 50% | 2022-04-10 | 10
Task 4 | Milestone |  |  | 2022-05-03 | 1 | bar: T
Task 5 | Med Risk |  | 10% | 2022-04-19 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-04-19 | 13
Task 2 | On Track |  | 50% | 2022-04-21 | 9
Task 3 | Low Risk |  | 33% | 2022-04-26 | 11
Task 4 | Milestone |  |  | 2022-04-28 | 1 | bar: T
Task 5 |  |  |  | 2022-04-29 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-04-28 | 4
Task 2 | Med Risk |  |  | 2022-05-01 | 14
Task 3 | On Track |  |  | 2022-05-16 | 6
Task 4 | Goal |  |  | 2022-05-20 | 3 | F: 2; S: 2; S: 2
Task 5 | Low Risk |  |  | 2022-04-19 | 19
TITLE 4
Task 1 |  |  |  | 2022-05-23 | 15
Task 2 |  |  |  | 2022-06-06 | 5
Task 3 | Milestone |  |  | 2022-07-18 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-04-13 |  |  |  |  | April | [13 empty] | May | [34 empty] | June
Scrolling Increment: | 5 | time axis 2022-04-18 to 2022-06-12
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-04-18 to 2022-06-12
TITLE 1
Task 1 | Goal | Name | 25% | 2022-04-13 | 3
Task 2 | Milestone |  |  | 2022-04-18 | 1 | bar: 2022-04-18
Task 3 | Low Risk |  | 50% | 2022-04-10 | 10
Task 4 | Milestone |  |  | 2022-05-03 | 1 | bar: 2022-05-03
Task 5 | Med Risk |  | 10% | 2022-04-19 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-04-19 | 13
Task 2 | On Track |  | 50% | 2022-04-21 | 9
Task 3 | Low Risk |  | 33% | 2022-04-26 | 11
Task 4 | Milestone |  |  | 2022-04-28 | 1 | bar: 2022-04-28
Task 5 |  |  |  | 2022-04-29 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-04-28 | 4
Task 2 | Med Risk |  |  | 2022-05-01 | 14
Task 3 | On Track |  |  | 2022-05-16 | 6
Task 4 | Goal |  |  | 2022-05-20 | 3 | 2022-05-20: 2; 2022-05-21: 2; 2022-05-22: 2
Task 5 | Low Risk |  |  | 2022-04-19 | 19
TITLE 4
Task 1 |  |  |  | 2022-05-23 | 15
Task 2 |  |  |  | 2022-06-06 | 5
Task 3 | Milestone |  |  | 2022-07-18 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Sprint 1
Sprint 1
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Caleb Knapp
Sprint Start Date: | 2022-01-25 |  |  |  |  | January | [6 empty] | February | [27 empty] | March
Scrolling Increment: | 0 | time axis 2022-01-25 to 2022-03-21
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-01-25 to 2022-03-21
Sprint 1
Create Initial Requirements Document | On Track | All | 100% | 2022-01-25 | 8
To add more data, Insert new rows ABOVE this one

## Sprint 2
Sprint 2
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Caleb Knapp
Sprint Start Date: | 2022-02-02 |  |  |  |  | February | [27 empty] | March
Scrolling Increment: | 0 | time axis 2022-02-02 to 2022-03-29
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-02-02 to 2022-03-29
Sprint 2
Come up with name | On Track | All | 100% | 2022-02-02 | 3
Create master page | On Track | Caleb Knapp | 100% | 2022-02-07 | 3
Create landing page | On Track | Himprawa Khattri | 100% | 2022-02-12 | 4
Create user information database structures | On Track | Mason Phillips, Timothy de Jesus | 100% | 2022-02-02 | 4
Create user registration page | On Track | Himprawa Khattri, Caleb Knapp | 100% | 2022-02-02 | 4
Create user class | On Track | Caleb Knapp | 100% | 2022-02-08 | 2
Create cookie jar class | On Track | Caleb Knapp | 100% | 2022-02-06 | 1
Create data provider class | On Track | Caleb Knapp | 100% | 2022-02-04 | 2
To add more data, Insert new rows ABOVE this one

## Sprint 3
Sprint 3
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Caleb Knapp
Sprint Start Date: | 2022-02-16 |  |  |  |  | February | [13 empty] | March | [34 empty] | April
Scrolling Increment: | 0 | time axis 2022-02-16 to 2022-04-12
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-02-16 to 2022-04-12
Sprint 3
Make message framework | On Track | Mason Phillips, Timothy de Jesus | 100% | 2022-02-16 | 12
Create encryption framework | On Track | Mason Phillips, Caleb Knapp | 100% | 2022-02-16 | 11
User search feature | On Track | Timothy de Jesus, Himprawa Khattri | 100% | 2022-02-16 | 15
Create message dashboard | On Track | Himprawa Khattri | 100% | 2022-02-18 | 13
Sprint 4
One-on-one communication |  | Mason Phillips, Timothy de Jesus | 0% | 2022-03-02 | 7
Notification of new messages |  | Timothy de Jesus, Himprawa Khattri | 0% | 2022-03-09 | 3
Make admin dashboard |  | Mason Phillips, Himprawa Khattri | 0% | 2022-03-09 | 5
Make first presentation material |  | All |  | 2022-03-02 | 13
Sprint 5
Group communication |  | Mason Phillips, Timothy de Jesus | 0% | 2022-03-16 | 7
Ability to join multiple channels |  | All | 0% | 2022-03-23 | 4
Ability to break out from groups |  | Timothy de Jesus, Himprawa Khattri | 0% | 2022-03-27 | 3
Sprint 6
Shoulder surfing protection |  | Mason Phillips, Himprawa Khattri | 0% | 2022-03-30 | 14
User icons |  | Himprawa Khattri | 0% | 2022-03-30 | 14
Sprint 7
Optimize for mobile devices |  | All | 0% | 2022-04-13 | 14
Sprint 8
Make final presentation material |  | All | 0% | 2022-04-27 | 7
To add more data, Insert new rows ABOVE this one

## Sprint 4
Sprint 4
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Caleb Knapp
Sprint Start Date: | 2022-03-02 |  |  |  |  | March | [34 empty] | April
Scrolling Increment: | 0 | time axis 2022-03-02 to 2022-04-26
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-03-02 to 2022-04-26
Sprint 4
One-on-one communication | On Track | Mason Phillips, Timothy de Jesus | 100% | 2022-03-02 | 10
Notification of new messages | On Track | Timothy de Jesus, Himprawa Khattri | 100% | 2022-03-09 | 3
Make admin dashboard | On Track | Mason Phillips, Himprawa Khattri | 100% | 2022-03-09 | 5
Make first presentation material | On Track | All | 100% | 2022-03-02 | 11
To add more data, Insert new rows ABOVE this one

## Sprint 5
Sprint 5
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Caleb Knapp
Sprint Start Date: | 2022-03-16 |  |  |  |  | March | [20 empty] | April | [27 empty] | May
Scrolling Increment: | 0 | time axis 2022-03-16 to 2022-05-10
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-03-16 to 2022-05-10
Sprint 5
Group communication | On Track | Mason Phillips, Timothy de Jesus | 100% | 2022-03-16 | 14
Ability to join multiple channels | On Track | All | 100% | 2022-03-16 | 14
Shoulder surfing protection | On Track | Caleb Knapp, Mason Phillips | 100% | 2022-03-16 | 14
Implement profanity check API | On Track | Caleb Knapp | 100% | 2022-03-24 | 6
To add more data, Insert new rows ABOVE this one

## Sprint 6
Sprint 6
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Caleb Knapp
Sprint Start Date: | 2022-03-30 |  |  |  |  | March | [6 empty] | April | [27 empty] | May
Scrolling Increment: | 0 | time axis 2022-03-30 to 2022-05-24
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-03-30 to 2022-05-24
Sprint 6
User icons | Low Risk | Caleb Knapp | 10% | 2022-03-30 | 14
File sharing | On Track | Timothy de Jesus, Caleb Knapp | 95% | 2022-03-30 | 14
Admin chat features | On Track | Mason Phillips, Caleb Knapp | 90% | 2022-03-30 | 14
Normalize Site Layout | On Track | Himprawa Khattri, Timothy de Jesus, Caleb Knapp | 85% | 2022-03-30 | 14
To add more data, Insert new rows ABOVE this one

## Sprint 7
Sprint 7
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Caleb Knapp
Sprint Start Date: | 2022-04-13 |  |  |  |  | April | [20 empty] | May | [27 empty] | June
Scrolling Increment: | 0 | time axis 2022-04-13 to 2022-06-07
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-04-13 to 2022-06-07
Sprint 7
Optimize for mobile devices |  | All | 0% | 2022-04-13 | 14
To add more data, Insert new rows ABOVE this one

## Sprint 8
Sprint 8
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Caleb Knapp
Sprint Start Date: | 2022-04-27 |  |  |  |  | April | [6 empty] | May | [27 empty] | June
Scrolling Increment: | 0 | time axis 2022-04-27 to 2022-06-21
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-04-27 to 2022-06-21
Sprint 8
Make final presentation material |  | All | 0% | 2022-04-27 | 7
To add more data, Insert new rows ABOVE this one